## Overview
Status update as of today
Activity Type | Analysis | Mapping | Development | Testing for 9 locales | Testing for 48 locales
URLs | 92 | 92 | 92 | 87 | 67
Testing detail report
The above number refer to the activities which are completed. Please go to next tab to check on the activities in progress. | [5 empty] | Reports shared for test | 91
[6 empty] | 48 locales tested | 67
[6 empty] | 48 test in progress | 20
[6 empty] | 48 reports generation | 0
[6 empty] | 48 locales test to start | 0
[6 empty] | 9 locales test done | 0
[6 empty] | 9 locales test in progress | 4
[6 empty] | 9 locales test to start | 0
[6 empty] | Total | 91

## Details
Date | URL | Category | Total locales to be tested | Analysis | Mapping | Development | Testing | Overall Status | ETA
| http://www.cisco.com/c/en/us/solutions/collaboration/benefit.html | Benefits | 48 | Done | Done | Done | Done |  | 2016-01-05
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/benefit.html | Benefits | 48 | Done | Done | Done | Done |  | 2016-01-05 |  | Testing in progress
| http://www.cisco.com/c/en/us/solutions/service-provider/benefit.html | Benefits | 48 | Done | Done | Done | Done |  | 2016-01-05 |  | Rework
| http://www.cisco.com/c/en/us/products/unified-communications/benefit.html | Benefits | 48 | Done | Done | Done | Done |  | 2016-01-05 |  | On hold
| http://www.cisco.com/c/en/us/products/collaboration-endpoints/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | On track
| http://www.cisco.com/c/en/us/products/conferencing/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | Cannot meet ETA
| http://www.cisco.com/c/en/us/products/unified-communications/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | Lagging behind
| http://www.cisco.com/c/en/us/products/customer-collaboration/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03
| http://www.cisco.com/c/en/us/products/ios-nx-os-software/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03
| http://www.cisco.com/c/en/us/products/security/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | Locale Info
| http://www.cisco.com/c/en/us/solutions/collaboration/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | de_de
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | pt_br
| http://www.cisco.com/c/en/us/solutions/enterprise-networks/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | ja_jp
| http://www.cisco.com/c/en/us/products/security/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | zh_cn
2016-02-02 | http://www.cisco.com/c/en/us/solutions/collaboration/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Testing in progress for 9 locales. |  | 2015-12-03 | ru_ru
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | fr_fr
2015-12-03 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | en_gb
2015-12-07 | http://www.cisco.com/c/en/us/products/security/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11 | ar_ae
2015-12-07 | http://www.cisco.com/c/en/us/solutions/collaboration/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11 | es_mx
2015-12-07 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/products/collaboration-endpoints/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/conferencing/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/customer-collaboration/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/unified-communications/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/service-provider/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/collaboration/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/solutions-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/collaboration/architecture.html | Architecture | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/architecture.html | Architecture | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/architecture.html | Architecture | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-18 | http://www.cisco.com/c/en/us/products/index.html | R-Root | 48 | Done | Done | Done | Testing in progress
2015-12-18 | http://www.cisco.com/c/en/us/products/routers/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/cloud-systems-management/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/physical-security/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/service-listing.html | R-Service-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/service-listing.html | R-Service-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/service-listing.html | R-Service-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/solution-listing.html | R-Solution-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/solution-listing.html | R-Solution-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/solution-listing.html | R-Solution-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-28 | http://www.cisco.com/c/en/us/solutions/index.html | R-Root | 48 | Done | Done | Done | Testing in progress
2015-12-29 | http://www.cisco.com/c/en/us/products/routers/buyers-guide.html | Buyers-Guide | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-29 | http://www.cisco.com/c/en/us/products/wireless/buyers-guide.html | Buyers-Guide | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-30 | http://www.cisco.com/c/en/us/solutions/executive-perspectives/index.html | Buyers-Guide | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-29 | http://www.cisco.com/c/en/us/products/cloud-systems-management/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-12-29 | http://www.cisco.com/c/en/us/products/physical-security/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-06
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/benefit.html | R-Benefits | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/products/storage-networking/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/solution-listing.html | R-Solution-Listing | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/service-listing.html | R-Service-Listing | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-11
2015-01-05 | http://www.cisco.com/c/en/us/products/storage-networking/product-listing.html | R-Prod-Listing | 48 | Done | Done | Done | Done |  | 2016-01-11
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/index.html | R-Prod-Landing | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/products/servers-unified-computing/technology.html | R-Technology | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/training-events.html | Training-Events | 48 | Done | Done | Done | Done |  | 2016-01-08
2015-01-05 | http://www.cisco.com/c/en/us/partners.html | Partners | 48 | Done | Done | Done | Done |  | 2016-01-11
2015-01-07 | http://www.cisco.com/c/en/us/solutions/service-provider/mobile-internet/index.html | Sub-Cat | 48 | Done | Done | Done | Done |  | 2016-01-13
2015-01-07 | http://www.cisco.com/c/en/us/solutions/service-provider/network-infrastructure/index.html | Sub-Cat | 48 | Done | Done | Done | Done |  | 2016-01-13
2015-01-11 | http://www.cisco.com/web/about/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/solutions/trends/cloud/case-studies.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/solutions/trends/cloud/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/solutions/trends/iot/overview.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/solutions/trends/sdn/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/solutions/trends/cloud/private-cloud-hybrid-cloud-solutions.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/strategy/energy/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/strategy/retail/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/strategy/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-11 | http://www.cisco.com/web/midsize/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-12 | http://www.cisco.com/web/strategy/financial/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-12 | http://www.cisco.com/web/strategy/government/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-12 | http://www.cisco.com/web/strategy/manufacturing/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-12 | http://www.cisco.com/web/midsize/products_solutions.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-12 | http://www.cisco.com/web/solutions/trends/cloud/managed-cloud-services.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-13 | http://www.cisco.com/web/services/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-13 | http://www.cisco.com/web/services/order-services/index.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-13 | http://www.cisco.com/web/solutions/trends/iot/iot_services.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-13 | http://www.cisco.com/web/solutions/trends/iot/solutions.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-13 | http://www.cisco.com/web/solutions/trends/iot/iot-products.html | Web url | 48 | Done | Done | Done | Testing in progress for 48 locales.
2015-01-20 | http://www.cisco.com/c/en/us/solutions/service-provider/videoscape/index.html | Sub-Cat | 9 | Done | Done | Done
2015-01-20 | http://www.cisco.com/c/en/us/support/index.html | Support | 9 | Done | Done | Done | Testing in progress for 9 locales.
2015-01-25 | http://www.cisco.com/c/en/us/products/security/benefit.html | Benefits | 48 | Done | Done | Done | Done
2015-01-25 | http://www.cisco.com/c/en/us/products/security/technology.html | Technology | 48 | Done | Done | Done | Done
2015-01-25 | http://www.cisco.com/c/en/us/products/security/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done

## Pending URLs
URL | Category | Additional Comments
http://www.cisco.com/c/en/us/products/switches/benefit.html | R-Benefits | Redirected page
http://www.cisco.com/c/en/us/products/switches/technology.html | R-Technology | Redirected page
http://www.cisco.com/c/en/us/products/wireless/benefit.html | R-Benefits | Redirected page
http://www.cisco.com/cisco/web/solutions/small_business/index.html | Web url
http://www.cisco.com/web/ordering/root/index.html | Web url
http://www.cisco.com/web/solutions/trends/mobility/index.html | Web url | Redirected page
http://www.cisco.com/web/solutions/trends/iot/portfolio.html | Web url | Redirected page
http://www.cisco.com/web/solutions/trends/iot/why.html | Web url | 404 Error, followed by redirection
Total Pending URL to be migrated | 2
Not in scope/Redirected/No need to work | 6

## Rework
http://www.cisco.com/c/en/us/products/servers-unified-computing/benefit.html | R-Benefits
http://www.cisco.com/c/en/us/products/storage-networking/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/servers-unified-computing/solution-listing.html | R-Solution-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/service-listing.html | R-Service-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/storage-networking/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/servers-unified-computing/technology.html | R-Technology
http://www.cisco.com/web/midsize/index.html | Web url
http://www.cisco.com/web/strategy/energy/index.html | Web url
http://www.cisco.com/web/strategy/retail/index.html | Web url
http://www.cisco.com/web/midsize/index.html | Web url
http://www.cisco.com/web/strategy/financial/index.html | Web url
http://www.cisco.com/web/strategy/government/index.html | Web url
http://www.cisco.com/web/strategy/manufacturing/index.html | Web url
http://www.cisco.com/web/solutions/trends/iot/iot-products.html | Web url
http://www.cisco.com/web/solutions/trends/cloud/private-cloud-hybrid-cloud-solutions.html | Web url

## Final URLs
http://www.cisco.com/c/en/us/products/security/benefit.html | Benefits
http://www.cisco.com/c/en/us/products/switches/benefit.html | R-Benefits
http://www.cisco.com/c/en/us/products/wireless/benefit.html | R-Benefits
http://www.cisco.com/c/en/us/solutions/index.html | R-Root
http://www.cisco.com/c/en/us/solutions/service-provider/mobile-internet/index.html | Sub-Cat
http://www.cisco.com/c/en/us/solutions/service-provider/network-infrastructure/index.html | Sub-Cat
http://www.cisco.com/c/en/us/solutions/service-provider/videoscape/index.html | Sub-Cat
http://www.cisco.com/c/en/us/products/security/technology.html | Technology
http://www.cisco.com/c/en/us/products/cloud-systems-management/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/physical-security/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/routers/buyers-guide.html | Buyers-Guide
http://www.cisco.com/c/en/us/products/security/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/wireless/buyers-guide.html | Buyers-Guide
http://www.cisco.com/c/en/us/solutions/executive-perspectives/index.html | Buyers-Guide
http://www.cisco.com/c/en/us/products/servers-unified-computing/benefit.html | R-Benefits
http://www.cisco.com/c/en/us/solutions/collaboration/benefit.html | Benefits
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/benefit.html | Benefits
http://www.cisco.com/c/en/us/solutions/service-provider/benefit.html | Benefits
http://www.cisco.com/c/en/us/products/unified-communications/benefit.html | Benefits
http://www.cisco.com/c/en/us/products/collaboration-endpoints/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/conferencing/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/unified-communications/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/customer-collaboration/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/ios-nx-os-software/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/security/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/storage-networking/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/solutions/collaboration/index.html | Prod-Landing
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/index.html | Prod-Landing
http://www.cisco.com/c/en/us/solutions/enterprise-networks/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/security/solution-listing.html | Solution-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/solution-listing.html | R-Solution-Listing
http://www.cisco.com/c/en/us/solutions/collaboration/solution-listing.html | Solution-Listing
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/solution-listing.html | Solution-Listing
http://www.cisco.com/c/en/us/solutions/enterprise-networks/solution-listing.html | Solution-Listing
http://www.cisco.com/c/en/us/products/security/service-listing.html | Service-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/service-listing.html | R-Service-Listing
http://www.cisco.com/c/en/us/solutions/collaboration/service-listing.html | Service-Listing
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/service-listing.html | Service-Listing
http://www.cisco.com/c/en/us/solutions/enterprise-networks/service-listing.html | Service-Listing
http://www.cisco.com/c/en/us/products/collaboration-endpoints/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/conferencing/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/customer-collaboration/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/unified-communications/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/solutions/service-provider/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/storage-networking/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/solutions/collaboration/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/solutions/enterprise-networks/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/solutions/service-provider/solutions-listing.html | Solution-Listing
http://www.cisco.com/c/en/us/products/servers-unified-computing/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/solutions/service-provider/index.html | Prod-Landing
http://www.cisco.com/c/en/us/products/servers-unified-computing/technology.html | R-Technology
http://www.cisco.com/c/en/us/solutions/collaboration/architecture.html | Architecture
http://www.cisco.com/c/en/us/solutions/data-center-virtualization/architecture.html | Architecture
http://www.cisco.com/c/en/us/solutions/service-provider/architecture.html | Architecture
http://www.cisco.com/c/en/us/products/index.html | R-Root
http://www.cisco.com/c/en/us/products/routers/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/switches/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/wireless/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/cloud-systems-management/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/physical-security/index.html | R-Prod-Landing
http://www.cisco.com/c/en/us/products/routers/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/switches/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/wireless/product-listing.html | R-Prod-Listing
http://www.cisco.com/c/en/us/products/routers/service-listing.html | R-Service-Listing
http://www.cisco.com/c/en/us/products/switches/service-listing.html | R-Service-Listing
http://www.cisco.com/c/en/us/products/wireless/service-listing.html | R-Service-Listing
http://www.cisco.com/c/en/us/products/routers/solution-listing.html | R-Solution-Listing
http://www.cisco.com/c/en/us/products/switches/solution-listing.html | R-Solution-Listing
http://www.cisco.com/c/en/us/products/wireless/solution-listing.html | R-Solution-Listing
http://www.cisco.com/c/en/us/products/switches/technology.html | R-Technology
http://www.cisco.com/cisco/web/solutions/small_business/index.html
http://www.cisco.com/c/en/us/support/index.html
http://www.cisco.com/web/about/index.html
http://www.cisco.com/c/en/us/training-events.html
http://www.cisco.com/web/midsize/index.html
http://www.cisco.com/web/midsize/products_solutions.html
http://www.cisco.com/web/ordering/root/index.html
http://www.cisco.com/c/en/us/partners.html
http://www.cisco.com/web/services/index.html
http://www.cisco.com/web/services/order-services/index.html
http://www.cisco.com/web/solutions/trends/cloud/case-studies.html
http://www.cisco.com/web/solutions/trends/cloud/index.html
http://www.cisco.com/web/solutions/trends/cloud/managed-cloud-services.html
http://www.cisco.com/web/solutions/trends/cloud/private-cloud-hybrid-cloud-solutions.html
http://www.cisco.com/web/solutions/trends/iot/iot_services.html
http://www.cisco.com/web/solutions/trends/iot/iot-products.html
http://www.cisco.com/web/solutions/trends/iot/overview.html
http://www.cisco.com/web/solutions/trends/iot/portfolio.html
http://www.cisco.com/web/solutions/trends/iot/solutions.html
http://www.cisco.com/web/solutions/trends/iot/why.html
http://www.cisco.com/web/solutions/trends/mobility/index.html
http://www.cisco.com/web/solutions/trends/sdn/index.html
http://www.cisco.com/web/strategy/energy/index.html
http://www.cisco.com/web/strategy/financial/index.html
http://www.cisco.com/web/strategy/government/index.html
http://www.cisco.com/web/strategy/index.html
http://www.cisco.com/web/strategy/manufacturing/index.html
http://www.cisco.com/web/strategy/retail/index.html