## Technogy
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
TECH1 | For RU_RU, Image was not loaded, where as all other locales imgae is loading. | http://www.cisco.com/web/RU/products/uc/technology.html | http://chard.cisco.com:4502/content/ru_ru/products/servers-unified-computing/technology.html | 2015-12-17 | closed | Ravi | Anudeep | Need to verify with shreya
TECH2 | Content and assests are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/UA/products/uc/technology.html | http://chard.cisco.com:4502/content/ru_ua/products/servers-unified-computing/technology.html | 2015-12-17 | closed | sasya | Anudeep | Need to verify with shreya
TECH3 | For en_ae, the source path is displaying as flows " <img src="/c/dam/global/en_ae/en/US/prod/collateral/ps10265/ps10276/unified_computing.jpg" alt="Unified Computing Technology">" | http://www.cisco.com/web/ME/products/uc/technology.html | http://chard.cisco.com:4502/content/en_ae/products/servers-unified-computing/technology.html | 2015-12-17 | closed | sasya | Surya/shreya
TECH4 | CISCO image is not displaying in the chard page tite-Surya | http://www.cisco.com/web/CH/fr/products/uc/technology.html | http://chard.cisco.com:4502/content/fr_ch/products/servers-unified-computing/technology.html | 2015-12-17 | Open | priyanka | Surya
TECH5 | Title in tha chard page is displaying as CISCO and in the WEB page it is displaying as Cisco Systems - Need to run on fresh livecopy | http://www.cisco.com/web/CH/fr/products/uc/technology.html | http://chard.cisco.com:4502/content/fr_ch/products/servers-unified-computing/technology.html | 2015-12-17 | Open | priyanka |  | Need to check with Chapa
TECH6 | Able to see an Error message in WEB URL below tsil borderd componenet. | http://www.cisco.com/web/IN/products/unified_computing/technology.html | http://chard.cisco.com:4502/content/en_in/products/servers-unified-computing/technology.html | 2015-12-17 | closed | ajay | anudeep
TECH7 | Tile component is UI is differnet when compared to Chard page where as content is same as Web URL | http://www.cisco.com/web/IN/products/unified_computing/technology.html | http://chard.cisco.com:4502/content/en_in/products/servers-unified-computing/technology.html | 2015-12-17 | closed | ajay | anudeep

## Product landing new
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PLN1 | 1.One of the image(INTEL) was not migrated at bottom of the page.-Resolved 2. PDF symbol is not displaying for one of the tail borderd list elements. ( on hold Due to migration from CSS) -Resolved 3.An Arrow symbol is not displaying in CTA element and Selective bars.- put it in general observations | http://www.cisco.com/web/ME/ar/products/uc/index.html | http://chard.cisco.com:4502/content/ar_ae/products/servers-unified-computing/index.html | 2015-12-17 | Open | ravi | saroja | Ned to discuss with Chapa.
PLN2 | 1.Report saying "Unable to update index list component." which is no where related to page.-Resolved 2. Content in the Selective bar is not same.-Resolved 3 . Other locales also have the same issue, - Resolved | http://www.cisco.com/web/ME/ar/solutions/service.html | http://chard.cisco.com:4502/content/ar_ae/solutions/service-provider/index.html | 2015-12-17 | Open | ravi | saroja
PLN3 | Hero component image is not migrated for the service unified computing index the image src is displaying as '/c/ru_ru/products/servers-unified-computing/index/_jcr_content/content_parsys/overview/layout-overview/gd12v1/gd12v1-right/hero_large/heropanel_0/image.img.jpg/1450346542685.jpg - Surya Note : same issue with the es_mx and pt_br locals | http://www.cisco.com/web/RU/products/uc/index.html | http://chard.cisco.com:4502/content/ru_ru/products/servers-unified-computing/index.html | 17-12-15 | open | priyanka | surya
PLN4 | pdf size and pdf image is missing for the right list components for the Экономическое обоснование для виртуальных управляемых сервисов hyper link - Resolved | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja | Need to add in outstanding list
PLN5 | Text component content mismatch - Fixed and need to checkin Note : same issue with the pt_br -Need reports | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN6 | content mismatch for the second spot light copmponet Экономия средств extra link is displaying after the content - to be restested Note : same issue with the pt_br (Gaste menos) | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN7 | spotlight components images are not migrated and src is displaying as src="/c/ru_ru/solutions/service-provider/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2_1/image.img.jpg/1450346576806.jpg" -Surya | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | surya
PLN8 | 1. links are missing for the selectorbar Приложения . Count mismatch 3 links are displaying in the chard page and 2 links are displaying in the web url for the -to be retested Приложения link -to be retested 2.links are missing for the selectorbar Рыночные тенденции . Count mismatch 5 links are displaying in the chard page and 4 links are displaying in the web url for the Рыночные тенденции link -to be retested Note : same issue with the es_mx and pt_br | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN9 | mismatch in the title of the page -Need to run on fresh livecopy Note : same issue with the ru_ru | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN10 | content mismatch for the selector bar links | http://www.cisco.com/web/LA/productos/uc/index.html | http://chard.cisco.com:4502/content/es_mx/products/servers-unified-computing/index.html | 17-12-15 | closed | priyanka | saroja
PLN11 | 1.pdf size is missing for right rail component.-closed(added in outstanding items) 2.mismatch in count of hero components.-Added in report 3.UI is different when compared to cisco page.- UI is similar to en/us page -Needs to inform chapa and put it in observations 4.we are able to see comment in report as "Mismatch in the right rail. List element is not found" but unable to find it in chard page.-closed 5..video icons are missing in images and images are missing from right rail components.- Video icons are coming from css and put it in observations, For image in tile bordered need to check with chapa as we are not having any property to set image path in tile bordered component. 6.we are able to see comment in report as "TileBordered Component description element not having any title in it ('p' is blank) " but unable to find it in chard page.-closed 7.content(2.05) is missing beside link for second right rail.-Fixed and need to checkin 8.image src is /c/ja_jp/products/servers-unified-computing/index/_jcr_content/content_parsys/overview/layout-overview/gd12v1/gd12v1-right/hero_large/heropanel_0/image.img.jpg/1450438903110.jpg-Surya 9.dot is missing behind the link for first right rail.- It is coming from css. (tile bordered) | http://www.cisco.com/web/JP/product/hs/ucs/index.html | http://chard.cisco.com:4502/content/ja_jp/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay
PLN12 | 1.we are able to view the following comment in report"Could not migrate tilebordered node. Count mis match as Element Count is 1 and node count is 3" but we have only one both in cisco and chard page.--closed 2.not able to view the following content "Explore all the latest service provider technology news" above inspire tail.-closed 3.mismatch in count of right rail and english content is migrated added comments in report-closed 4.English content is migrated in selector bars in dropdown values for links.-closed 5.The text beside the link for fourth spot light component is not migrated.-closed 6.able to view image src as "src="/c/ja_jp/solutions/service-provider/"-Surya 7.follow us images are not there on chard page. New observations as of 18.12.2015 after the build 1.image is not migrated for fourth spot light element.- update issue(QA) 2.folow us images are not migrated.-Surya 3.title mismatch in browser window.- Need to run on fresh livecopy | http://www.cisco.com/web/JP/solution/isp/index.html | http://chard.cisco.com:4502/content/ja_jp/solutions/service-provider/index.html?cq_ck=1450352564001 | 17.12.2015 | open | Ajay
PLN13 | 1.video icons are missing in images-Video icons are coming from css. Put it in observations list 2.pdf symbol is missing in right panels.-Need to add in observations list 3.intel image is not migrated.-closed 4.image src is /c/en_gb/products/servers-unified-computing/ for hero components.-surya | http://www.cisco.com/cisco/web/UK/products/unified_computing/index.html | http://chard.cisco.com:4502/content/en_gb/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay
PLN14 | 1.one link is missing for first selector bar -closed 2.Extra contents are displaying for third and fourth selector bar-closed 3.content is missing "Explore all the latest service provider technology news" under trending now.-Fixed and need to checkin 4.follow us images are not there on chard page.-surya 5.image src is "src="/c/en_gb/solutions/service-provider/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2/image.img.jpg/1450346476177.jpg" for all images. - surya 6.mismatch in count of right rails and english content is migrated-closed | http://www.cisco.com/cisco/web/UK/solutions/sp/sp_home.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/index.html | 17.12.2015 | open | Ajay
PLN15 | 1.pdf size is missing for right rail component.-closed 2.mismatch in the count of right rail.-closed 3.UI is different when compared to cisco page.-UI is similar to en/us page -Needs to inform chapa and put it in observations 4.video icons are missing in images -Video icons are coming from css. Put it in observations list 5.cisco image is missing.-surya 6.image src is /c/zh_cn/products/servers-unified-computing/index/_jcr_content/content_parsys/overview/layout-overview/gd12v1/gd12v1-right/hero_large/heropanel_0/image.img.jpg/1450346326145.jpg for hero components.-surya getting extra comment as "TileBordered Component description element not found" in report -Fixed and need to checkin | http://www.cisco.com/web/CN/products/products_netsol/ucs/index.html | http://chard.cisco.com:4502/content/zh_cn/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay
PLN16 | 1.Extra contents are displaying for third and fourth selector bar.-closed 2.the content "扩大盈利，降低运营开支，提升灵活性，借此让服务供应商的业务部署就位，稳健成长。在思科，我们已帮助几十家跨国服务供应商捕捉到在物联网下催生的众多发展机遇。" is not displaying on chard page.-Fixed and need to checkin 3.pdf symbol is missing.Add it in observations 4.meta title mismatch.-should run on fresh live copy 5.image src is "src="/c/zh_cn/solutions/service-provider/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2_0/gd12v2-left/hero_large/heropanel_2/image.img.jpg/1450346349088.jpg" for all images.-surya 6.displaying extra link for second spot light component-closed | http://www.cisco.com/web/CN/solutions/sp/index.html | http://chard.cisco.com:4502/content/zh_cn/solutions/service-provider/index.html | 17.12.2015 | open | Ajay
PLN17 | content under the Tendencias actuales link is not present in the chard page - Fixed and need to checkin | http://www.cisco.com/web/LA/soluciones/sp/index.html | http://chard.cisco.com:4502/content/es_mx/solutions/service-provider/index.html | 18/12/15 | open | priyanka
PLN18 | 1.One of the image(INTEL) was not migrated at bottom of the page. - to be Retested 2. PDF symbol is not displaying for one of the tail borderd list elements. ( on hold Due to migration from CSS) - need to be added observations list 3.An Arrow symbol is not displaying in CTA element and Selective bars. -need to be added observations list 4. Selector bar icons are not being dispalyed-need to be added observations list 5 . Other locales also have the same issue, | http://www.cisco.com/web/FR/products/uc/index.html | http://chard.cisco.com:4502/content/fr_fr/products/servers-unified-computing/index.html?cq_ck=1450444784002 | 2015-12-18 | Open | Sasya | Saroja
|  | http://www.cisco.com/web/FR/solutions/sp/index.html | http://chard.cisco.com:4502/content/fr_fr/solutions/service-provider/index.html | 2015-12-18 | Open | Sasya | Saroja

## Architecture
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
ARK1 | 1. In Tile bordered component(أحدث خطة للبنية), Few text is displaying as Link in chard page, where as it is a simple text in WEB URL 2. Report says image doesn't exist, in chard page we are seeing PDF symbol images are not migrated, with the sorce path." src="/assets/x/i/1365_16.png"". which is same as WEB URL. | http://www.cisco.com/web/ME/ar/solutions/collaboration/architecture.html | http://chard.cisco.com:4502/content/ar_ae/solutions/collaboration/architecture.html | 2015-12-17 | closed | Ravi | Aziz | Need to check with chapa on 1st item
ARK2 | heading of the page is not displaying Note : same issue for all the loclas | http://www.cisco.com/web/LA/soluciones/collaboration/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/collaboration/architecture.html | 2015-12-18 | closed | priyanka | Aziz
ARK3 | PDF images are not present for the list elements and tile bordered elements Note : same issue for all the locals | http://www.cisco.com/web/LA/soluciones/collaboration/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/collaboration/architecture.html | 2015-12-17 | open | priyanka | Aziz
ARK4 | Mismatch in the list elements but report it is mentioned that List node found for respective element on locale page | http://www.cisco.com/web/BR/solucoes/collaboration/architecture.html | http://chard.cisco.com:4502/content/pt_br/solutions/collaboration/architecture.html | 2015-12-18 | closed | priyanka | Aziz
ARK5 | 1.content "全体を見渡して考え、段階的に構築" is missing from chard page. 2.pdf symbol is missing. 3.Getting extra section as " design zone" on chard page. | http://www.cisco.com/web/JP/solution/collaboration/architecture.html | http://chard.cisco.com:4502/content/ja_jp/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK6 | 1. page title is missing. 2.pdf symbol is missing. 3.The link under the resources is missing. | http://www.cisco.com/cisco/web/UK/solutions/collaboration/architecture.html | http://chard.cisco.com:4502/content/en_gb/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK7 | 1. page title is missing. 2.pdf symbol is missing. 3.The link under the resources is missing. | http://www.cisco.com/web/CN/solutions/collaboration/collab_architecture.html | http://chard.cisco.com:4502/content/zh_cn/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK8 | 1. Mismatch in the content of the pdf size in chard page it is showing as (PDF - 467 KB) where as in the chard page it is showing as (PDF , 467 KB) 2.PDF images are missing Note : same issue with other locals | http://www.cisco.com/web/LA/soluciones/sp/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/service-provider/architecture.html | 2015-12-18 | open | priyanka | vidhya
ARK9 | most of the content is missing in the chard page | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK10 | In report it is mentioned that the image doesnot exists but we can able to see the image | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK11 | link is missing in the right trail component Admita una infraestructura convergente | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK12 | PDF size is missing in the chard page | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK13 | 1.Pdf symbol is missing | http://www.cisco.com/cisco/web/UK/solutions/sp/architecture.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/architecture.html | 2015-12-18 | open | Ajay | vidhya
ARK14 | 1.content "В глобальной сети функции механизма координации выполняет Cisco WAN Automation Engine is missing. 2.pdf symbols are missing. 3.ui is different when compared to cisco page. | http://www.cisco.com/web/RU/solutions/sp/architecture.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/architecture.html | 2015-12-18 | open | Ajay | vidhya

## Solution listing New
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SLN1 | Allignment issue for third image.- Put it in obeservations | http://www.cisco.com/cisco/web/UK/solutions/sp/solutions-listing.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/solutions-listing.html | 2015-12-17 | open | Ajay
SLN2 | Reports are not generated for ja_jp and zh_cn - Resolved |  |  | 2015-12-18 | open | Ajay
SLN3 | mismatch in the title of the page Need to run on fresh livecopy Note : same issue with es_mx | http://www.cisco.com/web/RU/solutions/sp/solutions-listing.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/solutions-listing.html | 2015-12-19 | open | priyanka
SLN4 | images are not alligned properly -Put it in obeservations | http://www.cisco.com/web/LA/soluciones/sp/solutions-listing.html | http://chard.cisco.com:4502/content/es_mx/solutions/service-provider/solutions-listing.html | 2015-12-20 | open | priyanka
SLN5 | mismatch in the url - Resolved | http://www.cisco.com/web/BR/solucoes/sp/index.html | http://chard.cisco.com:4502/content/pt_br/solutions/service-provider/solutions-listing.html | 2015-12-21 | open | priyanka

## Product landing old
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PL1 | For de_de, hero component panel images are not migatred in chard page when compared with WEB URL -Surya | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | TBD | Sasya | suryakanth | url have /en/us hence they are not migrated and expcting the same image should exists in chard.
|  | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | TBD | Sasya | suryakanth | url have /en/us hence they are not migrated and expcting the same image should exists in chard.
|  | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | TBD | Sasya | suryakanth | url have /en/us hence they are not migrated and expcting the same image should exists in chard.
PL2 | For de_de, in report its mentioned as Custom Head title not set but when compared with chard page, But we are seeing the Actual title same as WEB URL.- Fixed | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/voice/index.html | http://chard.cisco.com:4502/content/de_de/products/unified-communications/index.html?cq_ck=1450354916073 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/webex/index.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/index.html?cq_ck=1450353056792 | 2015-12-17 | Open | Sasya |  | NEED to check with CHAPA.
PL3 | For de_de, drawer component image source is displaying as "src="/c/de_de/products/collaboration-endpoints/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/drawers_container_0/drawerspanel_0/drawers-image.img.jpg/1450346943595.jpg" -Surya | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL4 | For de_de, "isco IP-Telefon der Serie 7800" subdrawer component image source is displaying as "src="/c/de_de/products/collaboration-endpoints/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/drawers_container_0/drawerspanel_0/drawers-image.img.jpg/1450346943595.jpg"-Surya | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL5 | For de_de, html blob component image not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Re-test | Sasya | suryakanth | no code written to migrate the dam. Updated the code.
|  | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Re-test | Sasya | suryakanth | Not an issue since no html blob found on web publisher to migrate.
|  | http://www.cisco.com/web/DE/products/webex/index.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/index.html?cq_ck=1450353056792 | 2015-12-17 | Re-test | Sasya | suryakanth | Not an issue since no html blob found on WEM publisher to migrate.
|  | http://www.cisco.com/web/DE/products/voice/index.html | http://chard.cisco.com:4502/content/de_de/products/unified-communications/index.html?cq_ck=1450354916073 | 2015-12-17 | Re-test | Sasya | suryakanth | no code written to migrate the dam. Updated the code.
PL6 | For de_de, image path is "src="http://www.static-cisco.com/assets/prod/col/img/finesse_100x80.jpg" | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Re-test | Sasya | suryakanth | no code written to migrate the dam. Updated the code.
PL7 | Follow Us images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.
|  | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.
PL8 | First grid elements image are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | TBD | Sasya | suryakanth | url have /c/dam hence they are not migrated and expcting the same image should exists in chard.
PL9 | In security page in 2nd grid elements bottom links are missing when compared with WEB URL | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
PL10 | For de_de image path is being displayed as "src="/c/de_de/products/storage-networking/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2_0/gd12v2-left/spotlight_large_v2/image.img.jpg/1450347273602.jpg" Note: Same issue with All the images | http://www.cisco.com/web/DE/products/storage/index.html | http://chard.cisco.com:4502/content/de_de/products/storage-networking/index.html | 2015-12-17 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL11 | For de_de image path is being displayed as "/c/de_de/products/security/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2_0/gd12v2-left/hero_large/heropanel_1/image.img.jpg/1450347224839.jpg" Note: Same issue with All the images | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL12 | For de_de image path is dispalyed as "src="/c/de_de/solutions/data-center-virtualization/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2/image.img.jpg/1450347309419.jpg" Note : Same issue with All images | http://www.cisco.com/web/DE/solutions/datacenter/index.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/index.html | 2015-12-17 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL13 | Selector bar icons are not being dispalyed in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/index.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/index.html | 2015-12-17 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.
|  | http://www.cisco.com/web/DE/products/storage/index.html | http://chard.cisco.com:4502/content/de_de/products/storage-networking/index.html | 2015-12-17 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.
PL14 | For de_de HTML Banner component is not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/borderless/index.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/index.html?cq_ck=1450418947309 | 2015-12-18 | Open | Sasya
PL15 | For de_de there is miss match between chard page title and WEB URL title | http://www.cisco.com/web/DE/solutions/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/index.html?cq_ck=1450419985240 | 2015-12-18 | Open | Sasya
PL16 | For de_de image path is displaying as "src="/c/de_de/solutions/enterprise-networks/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/hero_large/heropanel_2/image.img.jpg/1450347328878.jpg" Note- Same issue with All images | http://www.cisco.com/web/DE/solutions/borderless/index.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/index.html | 2015-12-19 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
PL17 | For de_de image path is displaying as "src="/c/de_de/solutions/collaboration/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/hero_large/heropanel_1/image.img.jpg/1450347358560.jpg" Note - Same issue with all images | http://www.cisco.com/web/DE/solutions/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/index.html | 2015-12-20 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity

## Service Listing old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SL1 | Fo de_de image path is showing as "/c/de_de/solutions/collaboration/service-listing/_jcr_content/content_parsys/services/layout-services/gd21v1/gd21v1-mid/spotlight_medium/image.img.jpg/1450348702268.jpg" - Surya Note - Same issue with All images | http://www.cisco.com/web/DE/solutions/collaboration/services.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/service-listing.html?cq_ck=1450429964572 | 2015-12-18 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
SL2 | For de_de the content is displying below the image instead of beside the image in chard page when compare dwith WEB URL - UI is similar to en/us page | http://www.cisco.com/web/DE/solutions/collaboration/services.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/service-listing.html?cq_ck=1450429964572 | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/borderless/services.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/service-listing.html | 2015-12-18 | Open | Sasya
SL3 | PDF image are missing in 1st grid element when compared with WEB URL- put it in the obsevations list | http://www.cisco.com/web/DE/products/unified_computing/services.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL4 | Bottom grid elements are not alligned properly when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL5 | Content mis match for 1st bottom grid element in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL6 | Bottom second grid element last text, link allignment is different when compared to WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/borderless/services.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/service-listing.html | 2015-12-18 | Open | Sasya
SL7 | Follow Us image not being dispalyed in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/products/security/services.html | http://chard.cisco.com:4502/content/de_de/products/security/service-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.
SL8 | Im age path is being dispalye as "src="/c/de_de/products/security/service-listing/_jcr_content/content_parsys/services/layout-services/gd21v1/gd21v1-mid/spotlight_large_v2_1/image.img.jpg/1450348761812.jpg" Note - Same issue for alla images | http://www.cisco.com/web/DE/products/security/services.html | http://chard.cisco.com:4502/content/de_de/products/security/service-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
SL9 | Image path is displaying as "src="/c/de_de/solutions/enterprise-networks/solution-listing/_jcr_content/content_parsys/solutions/layout-solutions/gd21v1/gd21v1-mid/spotlight_medium_v2/image.img.jpg/1450349468313.jpg" Note - Same issue for alla images | http://www.cisco.com/web/DE/solutions/borderless/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/solution-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity

## Product Listing old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PL1 | Page title is different for chard page and WEB URL page | http://www.cisco.com/web/DE/products/webex/products.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/product-listing.html | 2015-12-18 | Open | Sasya
PL2 | Drawer and Sub drawer Components images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/unified_computing/products.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/product-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | Image are being rendered from css. Need to update css. Tested by updating css file in firebug, working fine.

## Solution listing Old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SLN1 | For de_de the content is displying below the image instead of beside the image in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/products/security/solutions.html | http://chard.cisco.com:4502/content/de_de/products/security/solution-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/unified_computing/solutions.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/solution-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | Open | Sasya
SLN2 | Image path id displaying as " src="http://www.static-cisco.com/assets/sol/uc/images/cali_vid240x200.jpg" | http://www.cisco.com/web/DE/products/unified_computing/solutions.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/solution-listing.html?cq_ck=1450434227479 | 2015-12-18 | Re-test | Sasya | suryakanth | no code written to migrate the dam. Updated the code.
SLN3 | Bottom elements allignment is different in chared page when compared to WEB URL | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | Open | Sasya
SLN4 | Image pathe is displaying as "src="/c/de_de/solutions/collaboration/solution-listing/_jcr_content/content_parsys/solutions/layout-solutions/gd21v1/gd21v1-mid/spotlight_medium_4/image.img.jpg/1450349431900.jpg" | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | image is migrated propertly. Issue is with the component rendition, the image is being rendered with the content path instead of image path. OOTB functinlaity
SLN5 | Hero panel images not migrated in chard when compare dwith WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/solution-listing.html | 2015-12-18 | Open | Sasya
SLN6 | For spotlight images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/solution-listing.html | 2015-12-18 | TBD | Sasya | suryakanth | url have /c/dam hence they are not migrated and expcting the same image should exists in chard.

## Benifits
Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments