## Overview
Status update as of today
Activity Type | Analysis | Mapping | Development | Testing
URLs | 58 | 58 | 37 | 33
The above number refer to the activities which are completed. Please go to next tab to check on the activities in progress.

## Details
Date | URL | Category | Total locales to be tested | Analysis | Mapping | Development | Testing | Overall Status | ETA
| http://www.cisco.com/c/en/us/products/servers-unified-computing/benefit.html | Benefits | 9 | Done | Done | In Progress |  |  | TBD
| http://www.cisco.com/c/en/us/solutions/collaboration/benefit.html | Benefits | 9 | Done | Done | Updation needed |  |  | TBD
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/benefit.html | Benefits | 9 | Done | Done | Updation needed |  |  | TBD
| http://www.cisco.com/c/en/us/solutions/service-provider/benefit.html | Benefits | 9 | Done | Done | Updation needed |  |  | TBD |  | Blocker(Chard down)
| http://www.cisco.com/c/en/us/products/unified-communications/benefit.html | Benefits | 9 | Done | Done | Updation needed |  |  | TBD |  | On hold
| http://www.cisco.com/c/en/us/products/collaboration-endpoints/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | On track
| http://www.cisco.com/c/en/us/products/conferencing/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | Cannot meet ETA
| http://www.cisco.com/c/en/us/products/unified-communications/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 |  | Lagging behind
| http://www.cisco.com/c/en/us/products/customer-collaboration/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03
| http://www.cisco.com/c/en/us/products/ios-nx-os-software/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | Locale Info
| http://www.cisco.com/c/en/us/products/security/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | de_de
| http://www.cisco.com/c/en/us/products/storage-networking/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | pt_br
| http://www.cisco.com/c/en/us/solutions/collaboration/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | ja_jp
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | zh_cn
| http://www.cisco.com/c/en/us/solutions/enterprise-networks/index.html | Prod-Landing | 48 | Done | Done | Done | Done |  | 2015-12-03 | ru_ru
| http://www.cisco.com/c/en/us/products/security/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | fr_fr
| http://www.cisco.com/c/en/us/products/servers-unified-computing/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | en_gb
| http://www.cisco.com/c/en/us/solutions/collaboration/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | ar_ae
| http://www.cisco.com/c/en/us/solutions/data-center-virtualization/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03 | es_mx
2015-12-03 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/solution-listing.html | Solution-Listing | 48 | Done | Done | Done | Done |  | 2015-12-03
2015-12-07 | http://www.cisco.com/c/en/us/products/security/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/products/servers-unified-computing/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/solutions/collaboration/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/service-listing.html | Service-Listing | 48 | Done | Done | Done | Done |  | 2015-12-11
2015-12-07 | http://www.cisco.com/c/en/us/products/collaboration-endpoints/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/conferencing/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/customer-collaboration/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/unified-communications/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/service-provider/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-07 | http://www.cisco.com/c/en/us/products/servers-unified-computing/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/products/storage-networking/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/collaboration/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-09 | http://www.cisco.com/c/en/us/solutions/enterprise-networks/product-listing.html | Product-Listing | 48 | Done | Done | Done | Done |  | 2015-12-15
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/solutions-listing.html | Solution-Listing | 48 | Done | Done | Done | In Progress(9 locales testing completed, rest in progress) |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/products/servers-unified-computing/index.html | Prod-Landing | 48 | Done | Done | Done | In Progress(9 locales testing completed, rest in progress) |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/index.html | Prod-Landing | 48 | Done | Done | Done | In Progress(9 locales testing completed, rest in progress) |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/products/servers-unified-computing/technology.html | Technology | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/collaboration/architecture.html | Architecture | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/data-center-virtualization/architecture.html | Architecture | 48 | Done | Done | Done | Done |  | 2015-12-22
2015-12-14 | http://www.cisco.com/c/en/us/solutions/service-provider/architecture.html | Architecture | 48 | Done | Done | Done | In Progress(9 locales testing completed, rest in progress) |  | 2015-12-22
2015-12-18 | http://www.cisco.com/c/en/us/products/index.html | R-Root | 9 | Done | Done |  |  |  | TBD
2015-12-18 | http://www.cisco.com/c/en/us/products/routers/index.html | R-Prod-Landing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/index.html | R-Prod-Landing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/index.html | R-Prod-Landing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/cloud-systems-management/index.html | R-Prod-Landing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/physical-security/index.html | R-Prod-Landing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/product-listing.html | R-Prod-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/product-listing.html | R-Prod-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/product-listing.html | R-Prod-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/service-listing.html | R-Service-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/service-listing.html | R-Service-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/service-listing.html | R-Service-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/routers/solution-listing.html | R-Solution-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/solution-listing.html | R-Solution-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/wireless/solution-listing.html | R-Solution-Listing | 9 | Done | Done | In Progress |  |  | TBD
2015-12-21 | http://www.cisco.com/c/en/us/products/switches/technology.html | R-Technology | 9 | Done | Done |  |  |  | TBD

## Pending URLs
http://www.cisco.com/c/en/us/products/security/benefit.html | Benefits
http://www.cisco.com/c/en/us/products/switches/benefit.html | Benefits
http://www.cisco.com/c/en/us/products/wireless/benefit.html | Benefits
http://www.cisco.com/c/en/us/solutions/index.html | R-Root
http://www.cisco.com/c/en/us/solutions/service-provider/mobile-internet/index.html | Sub-Cat
http://www.cisco.com/c/en/us/solutions/service-provider/network-infrastructure/index.html | Sub-Cat
http://www.cisco.com/c/en/us/solutions/service-provider/videoscape/index.html | Sub-Cat
http://www.cisco.com/c/en/us/products/security/technology.html | Technology
http://www.cisco.com/c/en/us/products/cloud-systems-management/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/physical-security/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/routers/buyers-guide.html | Buyers-Guide
http://www.cisco.com/c/en/us/products/security/product-listing.html | Product-Listing
http://www.cisco.com/c/en/us/products/wireless/buyers-guide.html | Buyers-Guide
http://www.cisco.com/c/en/us/solutions/executive-perspectives/index.html | Resp-B.Guide