## Product landing
Date | Variations | Page URL's | Dev ETA | Dev Remaining | Dev Unit testing | Testing ETA | Testing Remaining | Comments | Remaining development effort(To be filled by Chapa)
2015-11-23 | index-var1 | http://chard.cisco.com:4502/content/es_mx/products/collaboration-endpoints/index.html, http://chard.cisco.com:4502/content/es_mx/products/conferencing/index.html, http://chard.cisco.com:4502/content/es_mx/products/unified-communications/index.html | 16hr | 8hr
| index-var9 | http://chard.cisco.com:4502/content/es_mx/products/storage-networking/index.html | 8hr | 0hr
| index-var14 | http://chard.cisco.com:4502/content/es_mx/solutions/collaboration/index.html | 8r | 0hr
2015-11-24 | index-var3 | http://chard.cisco.com:4502/content/es_mx/products/customer-collaboration/index.html | 8hr | 0hr
| index-var5 | http://chard.cisco.com:4502/content/es_mx/products/ios-nx-os-software/index.html | 10hr | 2h
| index-var10 | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/index.html | 8hr | 0hr
| index-var1 |  | 8hr | 0hr
2015-11-25 | index-var6 | http://chard.cisco.com:4502/content/es_mx/products/security/index.html | 8 hr | 0hr
| index-var9 |  | 8hr | 0hr
| index-var11 | http://chard.cisco.com:4502/content/es_mx/solutions/enterprise-networks/index.html | 8hr | 2hr
2015-11-26 | All Variation testing & Bug fixing |  | 16 hr |  |  | 18 hr
2015-11-27 | All Variation testing & Bug fixing |  | 16hr |  |  | 27 hr
2015-11-28
2015-11-29
2015-11-30 | All Variation testing & Bug fixing |  | 16hr |  |  | 27 hr
2015-12-01 | All Variation testing |  |  |  |  | 27hr
2015-12-02 | All Variations testing
Note : All 10 urls for product landing with 48 locales wil be tested by tomorrow

## Solution Listing
Date | Variations | Page URL's | Dev ETA | Dev Remaining | Dev Unit testing | Testing ETA | Testing Remaining | Comments | Remaining development effort(To be filled by Chapa)
2015-12-01 | Solution-listing-var2 | http://chard.cisco.com:4502/content/en/us/products/servers-unified-computing/solution-listing.html,http://chard.cisco.com:4502/content/en/us/products/security/solution-listing.html | 8hr | 0hr | 2hr
| Solution-listing-var8 | http://chard.cisco.com:4502/content/en/us/solutions/data-center-virtualization/solution-listing.html | 8hr | 0hr | 2hr
2015-12-02
2015-12-03
2015-12-04
2015-12-05

## Benefits
Date | Variations | Page URL's | Dev ETA | Dev Remaining | Dev Unit testing | Testing ETA | Testing Remaining | Comments | Remaining development effort(To be filled by Chapa)
| benefit-var1 | http://chard.cisco.com:4502/content/en/us/products/servers-unified-computing/benefit.html
| benefit-var2 | http://chard.cisco.com:4502/content/en/us/solutions/service-provider/benefit.html
| benefit-var3 | http://chard.cisco.com:4502/content/en/us/products/unified-communications/benefit.html
http://chard.cisco.com:4502/content/en/us/solutions/data-center-virtualization/benefit.html
http://chard.cisco.com:4502/content/en/us/solutions/collaboration/benefit.html