## Technogy
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
TECH1 | For RU_RU, Image was not loaded, where as all other locales imgae is loading. | http://www.cisco.com/web/RU/products/uc/technology.html | http://chard.cisco.com:4502/content/ru_ru/products/servers-unified-computing/technology.html | 2015-12-17 | closed | Ravi | Anudeep | Need to verify with shreya
TECH2 | Content and assests are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/UA/products/uc/technology.html | http://chard.cisco.com:4502/content/ru_ua/products/servers-unified-computing/technology.html | 2015-12-17 | closed | sasya | Anudeep | Need to verify with shreya
TECH3 | For en_ae, the source path is displaying as flows " <img src="/c/dam/global/en_ae/en/US/prod/collateral/ps10265/ps10276/unified_computing.jpg" alt="Unified Computing Technology">" | http://www.cisco.com/web/ME/products/uc/technology.html | http://chard.cisco.com:4502/content/en_ae/products/servers-unified-computing/technology.html | 2015-12-17 | closed | sasya | Surya/shreya
TECH4 | CISCO image is not displaying in the chard page tite | http://www.cisco.com/web/CH/fr/products/uc/technology.html | http://chard.cisco.com:4502/content/fr_ch/products/servers-unified-computing/technology.html | 2015-12-17 | Open | priyanka | Surya
TECH5 | Title in tha chard page is displaying as CISCO and in the WEB page it is displaying as Cisco Systems | http://www.cisco.com/web/CH/fr/products/uc/technology.html | http://chard.cisco.com:4502/content/fr_ch/products/servers-unified-computing/technology.html | 2015-12-17 | Open | priyanka |  | Need to check with Chapa
TECH6 | Able to see an Error message in WEB URL below tsil borderd componenet. | http://www.cisco.com/web/IN/products/unified_computing/technology.html | http://chard.cisco.com:4502/content/en_in/products/servers-unified-computing/technology.html | 2015-12-17 | closed | ajay | anudeep
TECH7 | Tile component is UI is differnet when compared to Chard page where as content is same as Web URL | http://www.cisco.com/web/IN/products/unified_computing/technology.html | http://chard.cisco.com:4502/content/en_in/products/servers-unified-computing/technology.html | 2015-12-17 | closed | ajay | anudeep

## Product landing new
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PLN1 | 1.One of the image(INTEL) was not migrated at bottom of the page. 2. PDF symbol is not displaying for one of the tail borderd list elements. ( on hold Due to migration from CSS) 3.An Arrow symbol is not displaying in CTA element and Selective bars. 4 . Other locales also have the same issue, | http://www.cisco.com/web/ME/ar/products/uc/index.html | http://chard.cisco.com:4502/content/ar_ae/products/servers-unified-computing/index.html | 2015-12-17 | Open | ravi | saroja | Ned to discuss with Chapa.
PLN2 | 1.Report saying "Unable to update index list component." which is no where related to page. 2. Content in the Selective bar is not same. 3 . Other locales also have the same issue, | http://www.cisco.com/web/ME/ar/solutions/service.html | http://chard.cisco.com:4502/content/ar_ae/solutions/service-provider/index.html | 2015-12-17 | Open | ravi | saroja
PLN3 | Hero component image is not migrated for the service unified computing index the image src is displaying as '/c/ru_ru/products/servers-unified-computing/index/_jcr_content/content_parsys/overview/layout-overview/gd12v1/gd12v1-right/hero_large/heropanel_0/image.img.jpg/1450346542685.jpg Note : same issue with the es_mx and pt_br locals | http://www.cisco.com/web/RU/products/uc/index.html | http://chard.cisco.com:4502/content/ru_ru/products/servers-unified-computing/index.html | 17-12-15 | open | priyanka | surya
PLN4 | pdf size and pdf image is missing for the right list components for the Экономическое обоснование для виртуальных управляемых сервисов hyper link | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN5 | Text component content mismatch Note : same issue with the pt_br | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN6 | content mismatch for the second spot light copmponet Экономия средств extra link is displaying after the content Note : same issue with the pt_br (Gaste menos) | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN7 | spotlight components images are not migrated and src is displaying as src="/c/ru_ru/solutions/service-provider/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2_1/image.img.jpg/1450346576806.jpg" | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | surya
PLN8 | 1. links are missing for the selectorbar Приложения . Count mismatch 3 links are displaying in the chard page and 2 links are displaying in the web url for the Приложения link 2.links are missing for the selectorbar Рыночные тенденции . Count mismatch 5 links are displaying in the chard page and 4 links are displaying in the web url for the Рыночные тенденции link Note : same issue with the es_mx and pt_br | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN9 | mismatch in the title of the page Note : same issue with the ru_ru | http://www.cisco.com/web/RU/solutions/sp/index.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/index.html | 17-12-15 | open | priyanka | saroja
PLN10 | content mismatch for the selector bar links | http://www.cisco.com/web/LA/productos/uc/index.html | http://chard.cisco.com:4502/content/es_mx/products/servers-unified-computing/index.html | 17-12-15 | open | priyanka | saroja
| 1.pdf size is missing for right rail component. 2.mismatch in count of hero components. 3.mismatch in the content for second right rail. 4.UI is different when compared to cisco page. 5.we are able to see comment in report as "Mismatch in the right rail. List element is not found" but unable to find it in chard page. 6.video icons are missing in images and images are missing from right rail components. 7.we are able to see comment in report as "TileBordered Component description element not having any title in it ('p' is blank) " but unable to find it in chard page. 8.getting an extra section as "intel" in web url page. | http://www.cisco.com/web/JP/product/hs/ucs/index.html | http://chard.cisco.com:4502/content/ja_jp/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay
| 1.we are able to view the following comment in report"Could not migrate tilebordered node. Count mis match as Element Count is 1 and node count is 3" but we have only one both in cisco and chard page. 2.not able to view the following content "Explore all the latest service provider technology news" above inspire tail. 3.mismatch in count of right rail and english content is migrated. 4.English content is migrated in selector bars in dropdown values for links. 5.The text beside the link for fourth spot light component is not migrated. 6.able to view image src as "src="/c/ja_jp/solutions/service-provider/" 7.follow us images are not there on chard page. | http://www.cisco.com/web/JP/solution/isp/index.html | http://chard.cisco.com:4502/content/ja_jp/solutions/service-provider/index.html?cq_ck=1450352564001 | 17.12.2015 | open | Ajay
| 1.video icons are missing in images 2.pdf symbol is missing in right panels. 3.intel image is not migrated. 4.image src is /c/en_gb/products/servers-unified-computing/ for hero components. | http://www.cisco.com/cisco/web/UK/products/unified_computing/index.html | http://chard.cisco.com:4502/content/en_gb/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay
| 1.one link is missing for first selector bar . 2.Extra contents are displaying for third and fourth selector bar. 3.content is missing "Explore all the latest service provider technology news" under trending now. 4.follow us images are not there on chard page. 5.image src is "src="/c/en_gb/solutions/service-provider/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2/image.img.jpg/1450346476177.jpg" for all images. 6.mismatch in count of right rails and english content is migrated. | http://www.cisco.com/cisco/web/UK/solutions/sp/sp_home.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/index.html | 17.12.2015 | open | Ajay
| 1.pdf size is missing for right rail component. 2.mismatch in the count of right rail. 3.UI is different when compared to cisco page. 4.video icons are missing in images and images are missing from right rail components. 5.cisco image is missing. 6.image src is /c/zh_cn/products/servers-unified-computing/index/_jcr_content/content_parsys/overview/layout-overview/gd12v1/gd12v1-right/hero_large/heropanel_0/image.img.jpg/1450346326145.jpg for hero components. | http://www.cisco.com/web/CN/products/products_netsol/ucs/index.html | http://chard.cisco.com:4502/content/zh_cn/products/servers-unified-computing/index.html | 17.12.2015 | open | Ajay

## Architecture
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
ARK1 | 1. In Tile bordered component(أحدث خطة للبنية), Few text is displaying as Link in chard page, where as it is a simple text in WEB URL 2. Report says image doesn't exist, in chard page we are seeing PDF symbol images are not migrated, with the sorce path." src="/assets/x/i/1365_16.png"". which is same as WEB URL. | http://www.cisco.com/web/ME/ar/solutions/collaboration/architecture.html | http://chard.cisco.com:4502/content/ar_ae/solutions/collaboration/architecture.html | 2015-12-17 | closed | Ravi | Aziz | Need to check with chapa on 1st item
ARK2 | heading of the page is not displaying Note : same issue for all the loclas | http://www.cisco.com/web/LA/soluciones/collaboration/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/collaboration/architecture.html | 2015-12-18 | closed | priyanka | Aziz
ARK3 | PDF images are not present for the list elements and tile bordered elements Note : same issue for all the locals | http://www.cisco.com/web/LA/soluciones/collaboration/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/collaboration/architecture.html | 2015-12-17 | open | priyanka | Aziz
ARK4 | Mismatch in the list elements but report it is mentioned that List node found for respective element on locale page | http://www.cisco.com/web/BR/solucoes/collaboration/architecture.html | http://chard.cisco.com:4502/content/pt_br/solutions/collaboration/architecture.html | 2015-12-18 | closed | priyanka | Aziz
ARK5 | 1.content "全体を見渡して考え、段階的に構築" is missing from chard page. 2.pdf symbol is missing. 3.Getting extra section as " design zone" on chard page. | http://www.cisco.com/web/JP/solution/collaboration/architecture.html | http://chard.cisco.com:4502/content/ja_jp/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK6 | 1. page title is missing. 2.pdf symbol is missing. 3.The link under the resources is missing. | http://www.cisco.com/cisco/web/UK/solutions/collaboration/architecture.html | http://chard.cisco.com:4502/content/en_gb/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK7 | 1. page title is missing. 2.pdf symbol is missing. 3.The link under the resources is missing. | http://www.cisco.com/web/CN/solutions/collaboration/collab_architecture.html | http://chard.cisco.com:4502/content/zh_cn/solutions/collaboration/architecture.html | 2015-12-17 | closed | priyanka | Aziz
ARK8 | 1. Mismatch in the content of the pdf size in chard page it is showing as (PDF - 467 KB) where as in the chard page it is showing as (PDF , 467 KB) 2.PDF images are missing Note : same issue with other locals | http://www.cisco.com/web/LA/soluciones/sp/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/service-provider/architecture.html | 2015-12-18 | open | priyanka | vidhya
ARK9 | most of the content is missing in the chard page | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK10 | In report it is mentioned that the image doesnot exists but we can able to see the image | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK11 | link is missing in the right trail component Admita una infraestructura convergente | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK12 | PDF size is missing in the chard page | http://www.cisco.com/web/LA/soluciones/datacenter/architecture.html | http://chard.cisco.com:4502/content/es_mx/solutions/data-center-virtualization/architecture.html | 2015-12-18 | open | priyanka | bhavya
ARK13 | 1.Pdf symbol is missing | http://www.cisco.com/cisco/web/UK/solutions/sp/architecture.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/architecture.html | 2015-12-18 | open | Ajay | vidhya
ARK14 | 1.content "В глобальной сети функции механизма координации выполняет Cisco WAN Automation Engine is missing. 2.pdf symbols are missing. 3.ui is different when compared to cisco page. | http://www.cisco.com/web/RU/solutions/sp/architecture.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/architecture.html | 2015-12-18 | open | Ajay | vidhya

## Solution listing New
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SLN1 | Allignment issue for third image. | http://www.cisco.com/cisco/web/UK/solutions/sp/solutions-listing.html | http://chard.cisco.com:4502/content/en_gb/solutions/service-provider/solutions-listing.html | 2015-12-17 | open | Ajay
SLN2 | Reports are not generated for ja_jp and zh_cn |  |  | 2015-12-18 | open | Ajay
SLN3 | mismatch in the title of the page Note : same issue with es_mx | http://www.cisco.com/web/RU/solutions/sp/solutions-listing.html | http://chard.cisco.com:4502/content/ru_ru/solutions/service-provider/solutions-listing.html | 2015-12-19 | open | priyanka
SLN4 | images are not alligned properly | http://www.cisco.com/web/LA/soluciones/sp/solutions-listing.html | http://chard.cisco.com:4502/content/es_mx/solutions/service-provider/solutions-listing.html | 2015-12-20 | open | priyanka
SLN5 | mismatch in the url | http://www.cisco.com/web/BR/solucoes/sp/index.html | http://chard.cisco.com:4502/content/pt_br/solutions/service-provider/solutions-listing.html | 2015-12-21 | open | priyanka

## Product landing old
| Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PL1 | For de_de, hero component panel images are not migatred in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | Open | Sasya
PL2 | For de_de, in report its mentioned as Custom Head title not set but when compared with chard page, But we are seeing the Actual title same as WEB URL. | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/voice/index.html | http://chard.cisco.com:4502/content/de_de/products/unified-communications/index.html?cq_ck=1450354916073 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/webex/index.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/index.html?cq_ck=1450353056792 | 2015-12-17 | Open | Sasya |  | NEED to check with CHAPA.
PL3 | For de_de, drawer component image source is displaying as "src="/c/de_de/products/collaboration-endpoints/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/drawers_container_0/drawerspanel_0/drawers-image.img.jpg/1450346943595.jpg" | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
PL4 | For de_de, "isco IP-Telefon der Serie 7800" subdrawer component image source is displaying as "src="/c/de_de/products/collaboration-endpoints/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/drawers_container_0/drawerspanel_0/drawers-image.img.jpg/1450346943595.jpg" | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
PL5 | For de_de, html blob component image not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/telepresence/index.html | http://chard.cisco.com:4502/content/de_de/products/collaboration-endpoints/index.html?cq_ck=1450349558832 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/webex/index.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/index.html?cq_ck=1450353056792 | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/voice/index.html | http://chard.cisco.com:4502/content/de_de/products/unified-communications/index.html?cq_ck=1450354916073 | 2015-12-17 | Open | Sasya
PL6 | For de_de, image path is "src="http://www.static-cisco.com/assets/prod/col/img/finesse_100x80.jpg" | http://www.cisco.com/web/DE/products/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/products/customer-collaboration/index.html | 2015-12-17 | Open | Sasya
PL7 | Follow Us images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
PL8 | First grid elements image are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/ios-nx-os-software/index.html | http://chard.cisco.com:4502/content/de_de/products/ios-nx-os-software/index.html | 2015-12-17 | Open | Sasya
PL9 | In security page in 2nd grid elements bottom links are missing when compared with WEB URL | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
PL10 | For de_de image path is being displayed as "src="/c/de_de/products/storage-networking/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2_0/gd12v2-left/spotlight_large_v2/image.img.jpg/1450347273602.jpg" Note: Same issue with All the images | http://www.cisco.com/web/DE/products/storage/index.html | http://chard.cisco.com:4502/content/de_de/products/storage-networking/index.html | 2015-12-17 | Open | Sasya
PL11 | For de_de image path is being displayed as "/c/de_de/products/security/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2_0/gd12v2-left/hero_large/heropanel_1/image.img.jpg/1450347224839.jpg" Note: Same issue with All the images | http://www.cisco.com/web/DE/products/security/index.html | http://chard.cisco.com:4502/content/de_de/products/security/index.html | 2015-12-17 | Open | Sasya
PL12 | For de_de image path is dispalyed as "src="/c/de_de/solutions/data-center-virtualization/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/spotlight_large_v2/image.img.jpg/1450347309419.jpg" Note : Same issue with All images | http://www.cisco.com/web/DE/solutions/datacenter/index.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/index.html | 2015-12-17 | Open | Sasya
PL13 | Selector bar icons are not being dispalyed in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/index.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/index.html | 2015-12-17 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/storage/index.html | http://chard.cisco.com:4502/content/de_de/products/storage-networking/index.html | 2015-12-17 | Open | Sasya
PL14 | For de_de HTML Banner component is not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/borderless/index.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/index.html?cq_ck=1450418947309 | 2015-12-18 | Open | Sasya
PL15 | For de_de there is miss match between chard page title and WEB URL title | http://www.cisco.com/web/DE/solutions/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/index.html?cq_ck=1450419985240 | 2015-12-18 | Open | Sasya
PL16 | For de_de image path is displaying as "src="/c/de_de/solutions/enterprise-networks/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/hero_large/heropanel_2/image.img.jpg/1450347328878.jpg" Note- Same issue with All images | http://www.cisco.com/web/DE/solutions/borderless/index.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/index.html | 2015-12-19 | Open | Sasya
PL17 | For de_de image path is displaying as "src="/c/de_de/solutions/collaboration/index/_jcr_content/content_parsys/overview/layout-overview/gd12v2/gd12v2-left/hero_large/heropanel_1/image.img.jpg/1450347358560.jpg" Note - Same issue with all images | http://www.cisco.com/web/DE/solutions/collaboration/index.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/index.html | 2015-12-20 | Open | Sasya

## Service Listing old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SL1 | Fo de_de image path is showing as "/c/de_de/solutions/collaboration/service-listing/_jcr_content/content_parsys/services/layout-services/gd21v1/gd21v1-mid/spotlight_medium/image.img.jpg/1450348702268.jpg" Note - Same issue with All images | http://www.cisco.com/web/DE/solutions/collaboration/services.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/service-listing.html?cq_ck=1450429964572 | 2015-12-18 | Open | Sasya
SL2 | For de_de the content is displying below the image instead of beside the image in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/solutions/collaboration/services.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/service-listing.html?cq_ck=1450429964572 | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/borderless/services.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/service-listing.html | 2015-12-18 | Open | Sasya
SL3 | PDF image are missing in 1st grid element when compared with WEB URL | http://www.cisco.com/web/DE/products/unified_computing/services.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL4 | Bottom grid elements are not alligned properly when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL5 | Content mis match for 1st bottom grid element in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
SL6 | Bottom second grid element last text, link allignment is different when compared to WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/services.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/service-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/borderless/services.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/service-listing.html | 2015-12-18 | Open | Sasya
SL7 | Follow Us image not being dispalyed in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/products/security/services.html | http://chard.cisco.com:4502/content/de_de/products/security/service-listing.html | 2015-12-18 | Open | Sasya
SL8 | Im age path is being dispalye as "src="/c/de_de/products/security/service-listing/_jcr_content/content_parsys/services/layout-services/gd21v1/gd21v1-mid/spotlight_large_v2_1/image.img.jpg/1450348761812.jpg" Note - Same issue for alla images | http://www.cisco.com/web/DE/products/security/services.html | http://chard.cisco.com:4502/content/de_de/products/security/service-listing.html | 2015-12-18 | Open | Sasya
SL9 | Image path is displaying as "src="/c/de_de/solutions/enterprise-networks/solution-listing/_jcr_content/content_parsys/solutions/layout-solutions/gd21v1/gd21v1-mid/spotlight_medium_v2/image.img.jpg/1450349468313.jpg" Note - Same issue for alla images | http://www.cisco.com/web/DE/solutions/borderless/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/enterprise-networks/solution-listing.html | 2015-12-18 | Open | Sasya

## Product Listing old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
PL1 | Page title is different for chard page and WEB URL page | http://www.cisco.com/web/DE/products/webex/products.html | http://chard.cisco.com:4502/content/de_de/products/conferencing/product-listing.html | 2015-12-18 | Open | Sasya
PL2 | Drawer and Sub drawer Components images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/products/unified_computing/products.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/product-listing.html | 2015-12-18 | Open | Sasya

## Solution listing Old
Issue Number | Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments
SLN1 | For de_de the content is displying below the image instead of beside the image in chard page when compare dwith WEB URL | http://www.cisco.com/web/DE/products/security/solutions.html | http://chard.cisco.com:4502/content/de_de/products/security/solution-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/products/unified_computing/solutions.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/solution-listing.html | 2015-12-18 | Open | Sasya
|  | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | Open | Sasya
SLN2 | Image path id displaying as " src="http://www.static-cisco.com/assets/sol/uc/images/cali_vid240x200.jpg" | http://www.cisco.com/web/DE/products/unified_computing/solutions.html | http://chard.cisco.com:4502/content/de_de/products/servers-unified-computing/solution-listing.html?cq_ck=1450434227479 | 2015-12-18 | Open | Sasya
SLN3 | Bottom elements allignment is different in chared page when compared to WEB URL | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | Open | Sasya
SLN4 | Image pathe is displaying as "src="/c/de_de/solutions/collaboration/solution-listing/_jcr_content/content_parsys/solutions/layout-solutions/gd21v1/gd21v1-mid/spotlight_medium_4/image.img.jpg/1450349431900.jpg" | http://www.cisco.com/web/DE/solutions/collaboration/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/collaboration/solution-listing.html | 2015-12-18 | Open | Sasya
SLN5 | Hero panel images not migrated in chard when compare dwith WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/solution-listing.html | 2015-12-18 | Open | Sasya
SLN6 | For spotlight images are not migrated in chard page when compared with WEB URL | http://www.cisco.com/web/DE/solutions/datacenter/solutions.html | http://chard.cisco.com:4502/content/de_de/solutions/data-center-virtualization/solution-listing.html | 2015-12-18 | Open | Sasya

## Benifits
Issue | Web URL | Chard URL | Date | Status | Tester | Developer | Comments